## Eastfields - Tranche 1
Category | CPO Schedule Plot Number | FH or LH | Address | Comments
Non Resident Homeowners | 13 | LH | 45 Pains Close | This landlord owns 5 properties on the estate including 1 in Tranche 2. She has been reluctant to engage properly aside from allowing access for our surveyor to complete valuations of all 5 properties. We anticipate the initial notifications of the CPO will prompt her into engaging more fully. This is a 1 bed flat and we have not had any engagement with the tenants and are unclear what has been communicated with them.
| 15 | FH | 55 Pains Close | We are in conveyancing to complete the purchase of this property. However it was the subject of a court case to determine ownership and until the title is amended with HMLR then we cannot proceed to completion. This property was occupied by a very large inter-generational household. LBM Housing Options team found a home for the majority of the family but the adult children who have young children of their own still require re-housing (2 x 2 bed properties).
| 29 | FH | 95 Clay Avenue | Property owner's father lives in the property. He is elderly and in poor health. Our conversations with the owner have not proved positive and he has not agreed to sell. The father is adamant wishes to remain in property although living in a 3 storey town house does not appear to be safe for him due to his ill health. We discovered serious disrepair issues in the home. As as result of this and of the father's presentation, we have made a safeguarding alert to the social services team at LBM - no further action as a result of this as the Father has capacity. Have since had good conversation with both the father and the son, the former accepts that he needs to move so we are working with LBM to secure a new home for him that is suitable and in the right location. The son has indicated would sell back the property once the father is rehoused.
| 42 | LH | 69 Clay Avenue | Homeowner has only communicated sporadically. Had wanted to speak to LBM to discuss the CPO but officers were unable to reach her. We have recently made contact with her tenant who has a school age child. She had been trying to get the landlord and / or the letting agent to serve her with a s21 notice so she could approach LBM Housing Options. We have since emailed that team who have agreed to support her and made contact to arrange this.
Resident Homeowners | 14 | FH | 52 Pains Close | We are in discussions with the owners to find them a suitable home as temporary accommodation. They have started conveyancing. Once a home is found we can proceed to completion.
| 16 | FH | 58 Pains Close | Temporary accommodation identified and confirmed, are well progressed through conveyancing but some issues around completion date as family are currently overseas.
| 17 | FH | 60 Pains Close | We are in discussions with the owners to find them a suitable home as temporary accommodation. They have not yet started conveyancing. Once a home is found we can proceed to completion.
| 19 | FH | 73 Clay Avenue | Has not yet decided if he wishes to move away from the area or remain and go into temporary accommodation pending the new homes being built. He has had valuation which he is not satisfied with and obtained a valuation from his own surveyor. However this surveyor has vastly over estimated the value of the property with no supporting evidence so we have set out our offer clearly and await their response.
| 20 | FH | 76 Clay Avenue | This couple are in conveyancing and have identified temporary accommodation for them. We are waiting for adaptations to be made to the property in view of their age and disabilities.
| 24 | FH | 81 Clay Avenue | Property identified for temporary accommodation and they are in conveyancing due to complete 5.1.24
| 25 | FH | 82 Clay Avenue | Property identified for temporary accommodation and they are in conveyancing
| 28 | FH | 94 Clay Avenue | They are in conveyancing and a temporary accommodation property has been identified. Homeowner currently overseas, awaiting her return to complete sale.
| 30 | FH | 100 Clay Avenue | They are in conveyancing and temporary accommodation has been found with final works taking place. However recent information has come to light which suggests this is not a resident homeowner after all, we are carrying out further investigations but believe that he is not resident and will be proceeding on that basis.
| 32 | FH | 103 Clay Avenue | Homeowner is in conveyancing and a property for temporary accommodation has been provided. We are supporting to her to move with a packing service due to her age and vulnerability.
| 33 | FH | 104 Clay Avenue | Homeowner is in conveyancing and a property for temporary accommodation has been provided. We are supporting to her to move with a packing service due to her age and vulnerability.
| 35 | FH | 3 Thrupp Close | Have found him temporary accommodation and waiting for confirmation of his solicitor so can get into conveyancing.
| 48 | LH | 33 Pains Close | In conveyancing and property is ready to move into. Final paperwork to be completed and move arrange so can complete on sale.

## Eastfields - Tranche 2
Category | CPO Schedule Plot Number | FH or LH | Address | Comments
Non Resident Homeowners | 39 | FH | 19 Potter Close | This landlord owns 5 properties on the estate including 1 in Tranche 2. She has been reluctant to engage properly aside from allowing access for our surveyor to complete valuations of all 5 properties. We anticipate the initial notifications of the CPO will prompt her into engaging more fully.
| 41 | FH | 26 Pains Close | Currently in conveyancing but they do not yet have vacant posession so we cannot complete on the purchase. They have obtained a possession order and have a bailiff date of 22.1.24. Have contacted LBM Housing Options to advise of this.
| 47 | LH | 23 Pains Close | We have had negotiations with the landlord and are close to agreement to buy back but they are disputing the valuation of the property.
Resident Homeowners | 2 | FH | 2 Potter Close | Offered opportunity to sell back now and live in current home on licence until new homes are built. Planning to accept this offer and proceed.
| 3 | FH | 4 Potter Close | Offered opportunity to sell back now and live in current home on licence until new homes are built.
| 4 | LH | 34 Potter Close | Offered opportunity to sell back now and live in current home on licence until new homes are built.
| 8 | FH | 44 Potter Close | Offered opportunity to sell back now and live in current home on licence until new homes are built.
| 11 | FH | 14 Pains Close | Offered opportunity to sell back now and live in current home on licence until new homes are built.
| 38 | LH | 9 Potter Close | Offered opportunity to sell back now and live in current home on licence until new homes are built.
| 40 | LH | 35 Potter Close | Offered opportunity to sell back now and live in current home on licence until new homes are built.
| 43 | LH | 12 Potter Close | Offered opportunity to sell back now and live in current home on licence until new homes are built.
| 44 | LH | 21 Potter Close | Offered opportunity to sell back now and live in current home on licence until new homes are built.
| 45 | LH | 32 Potter Close | Offered opportunity to sell back now and live in current home on licence until new homes are built.
Owned by L&Q | 7 | FH | 43 Potter Close | Property is occupied. Ongoing negotiations and liaision with L&Q to complete mini-stock transfer. Due to complete by end of Dec 23
| 10 | FH | 8 Pains Close | Property is occupied. Ongoing negotiations and liaision with L&Q to complete mini-stock transfer. Due to complete by end of Dec 23

## High Path Phase 2
Category | CPO Schedule Plot Number | FH or LH | Address | Comments
Resident Homeowner | 26 & 38 | LH | 7 Lovell House | Original homeowner passed away in late 2022. Prior to her death her and her family had not substantively agreed to a deal. Since her passing, her son as beneficiary of her will has not been progressing matters. Most recent comms were that he would not allow access to the property for an accurate valuation until Clarion agreed to buy him a property of his choosing in an area of his choosing (or give him the financial equivalent).
| 41 | LH | 5 Marsh Court | Have made a number of attempts to assist the homeowner in the buyback process and have moved her on licence into her new home. She wishes to get a lawyer to assist her before she agrees any buyback deal and is insistent she does not need to sell her home back to us in order to get the replacement home deal.

## High Path Phase 3
Category | CPO Schedule Plot Number | FH or LH | Address | Comments
Non Resident Homeowner | 8 | FH | 11 Hayward Close | Have had discussions about valuation but offer not yet accepted. CPO schedule shows the residents as being Andrew Connelly, Timothy Hurrel, Ciorstaioh Nicol and Bart Levinsor, suggests this a HMO.
| 11 | FH | 14 Hayward Close | Have had discussions about valuation but offer not yet accepted. CPO schedule shows that the residents are Viktoria Matuz and Robert Balogh.
| 15 | FH | 1 Dowman Close | Have not yet had valuation, had query on CGT which has been answered but not engaging despite chasers. No information on occupiers.
| 17 | FH | 5 Dowman Close | Have not had valuation, despite chasers to agree access. No information on occupiers.
| 35 | LH | 14 Becket Close | Purchase price agreed and now in conveyancing. No information on occupiers.
| 50 | LH | 10 Gilbert Close | Is not yet in conveyancing. Having some issues with tenants. No information on occupiers.
| 3 | LH | 20 Gilbert Close | Homeowners are in conveyancing and one is moving to the replacement home. There are issues following divorce proceedings and division of assets.
| 10 | FH | 1 Hayward Close | Homeowner intends to move away and has confirmed intention to sell to us closer to the date of demolition.
| 12 | FH | 8 Hayward Close | Intends to move off the estate and is looking at possible options with buying with family to get the property she is looking for.
| 21 | FH | 4 Dowman Close | Does not meet criteria for replacement home but is trying to argue that this is incorrect.
| 18 | FH | 17 Dowman Close | Will be moving to replacement home which will be built in Phase 2.
| 19 | FH | 19 Dowman Close | Will be moving to replacement home which will be built in Phase 2.
| 23 | FH | 12 Dowman Close | Will be moving to replacement home which will be built in Phase 2.
| 36 | LH | 16 Becket Close | Indicated wish to take up replacement home offer but are struggling to find mortgage deal.
| 43 | LH | 18 Gilbert Close | Have put in objection to CPO (x3). However unclear what option they wish to take up. No response to letters or offers to arrange valuation. Continue to hold replacement home for them.

## Ravensbury
Category | CPO Schedule Plot Number | FH or LH | Address | Comments
Resident Homeowner |  | FH | 217 Morden Road | Have put in objection to CPO (x2). Would like various minor amends to the replacement home to be done, which Clarion have agreed to. Also wanted a social rent home for their son which cannot be agreed to. Have agreed to offer him first refusal of a shared ownership property on the estate. Agreement for this going through governance. Once approved can create HoT for him to sign off on and remove objection.